## Project Plan
Lead | Task | Year 1 Q1 | Q2 | Q3 | Q4 | Year 2 Q1 | Q2 | Q3 | Q4 | Year 3 Q1 | Q2 | Q3 | Q4
Broadband asset database
Conduit inventory
Wireless site inventory
Existing right of way inventory
Pole route survey
Fiber route & node survey
Conduit validation
Wireless facilities inventory
Carrier briefings
Map layer collection & review
Map layer development
Database architecture
Database development
Information access policy development
Expert group review
Model policy development
General plans review
Development ordinances/policies survey
Trench & conduit ordinances/policies survey
Benchmark research and analysis
Model policy drafting
Model policy peer review
Policy draft presentations & briefings
Carrier briefings
Policy map layer development
Expert group review
Deployment support platform
Public works workshop
Public works access & interface scoping
Economic development workshop
Economic development access & interface scoping
Access & interface peer review
Data set & map layer peer review
Platform beta
Platform release
Demographic & economic data collection
Broadband coverage data collection
Map layer revision & maintenance
Access & interface design
Platform development
Platform finalization
CASF partner development
Platform marketing
Expert group review
Broadband adoption support
Santa Cruz County scoping & design
San Benito County scoping & design
Santa Cruz County implementation
San Benito County implementation
Santa Cruz County operations
San Benito County operations
Administration
Executive committee oversight
Financial management
Key
Economic development analyst
GIS analyst
Infrastructure specialist
Network specialist
Database developer
Executive committee/expert groups/subs
http://www.tellusventure.com/community/california/

## Budget
Item | Lead | Year 1 Grant | Year 1 Match | Year 1 Total | Year 2 Grant | Year 2 Match | Year 2 Total | Year 3 Grant | Year 3 Match | Year 3 Total | Grand Total
Personnel
Economic development analyst |  | 40000 |  | 40000 | 40000 |  | 40000 | 40000 |  | 40000 | 120000
GIS analyst |  | 20000 |  | 20000 | 20000 |  | 20000 | 20000 |  | 20000 | 60000
Infrastructure specialist |  | 40000 |  | 40000 | 20000 |  | 20000 | 20000 |  | 20000 | 80000
Network specialist |  | 10000 |  | 10000 | 10000 |  | 10000 | 10000 |  | 10000 | 30000
Executive committee |  |  | 36000 | 36000 |  | 36000 | 36000 |  | 36000 | 36000 | 108000
Technical expert group |  |  | 10000 | 10000 |  | 10000 | 10000 |  | 10000 | 10000 | 30000
Economic development expert group |  |  | 10000 | 10000 |  | 10000 | 10000 |  | 10000 | 10000 | 30000
Out of Pocket
Web/database development |  | 5000 |  | 5000 | 20000 |  | 20000 | 20000 |  | 20000 | 45000
IT and licenses |  | 1000 | 24000 | 25000 | 1000 | 12000 | 13000 | 1000 | 12000 | 13000 | 51000
Public works/highway review |  | 250 | 250 | 500 | 5000 | 2000 | 7000 | 500 | 500 | 1000 | 8500
Economic development review |  | 250 | 250 | 500 | 500 | 500 | 1000 | 5000 | 2000 | 7000 | 8500
Carrier briefings |  | 250 | 250 | 500 | 250 | 250 | 500 | 250 | 250 | 500 | 1500
CASF partner development |  |  |  | 0 |  | 30000 | 30000 |  |  | 0 | 30000
Platform marketing |  |  |  | 0 |  |  | 0 |  | 30000 | 30000 | 30000
Expert group review |  | 500 | 500 | 1000 | 500 | 500 | 1000 | 500 | 500 | 1000 | 3000
Adoption
Santa Cruz adoption program |  | 10000 | 40000 | 50000 | 10000 | 20000 | 30000 | 10000 | 20000 | 30000 | 110000
San Benito adoption program |  | 10000 | 40000 | 50000 | 10000 | 20000 | 30000 | 10000 | 20000 | 30000 | 110000
Overhead
Fiscal oversight (8%) |  | 12000 | 12900 | 24900 | 12000 | 11300 | 23300 | 12000 | 11300 | 23300 | 71500
Legal and fees |  | 500 | 1000 | 1500 | 500 | 500 | 1000 | 500 | 500 | 1000 | 3500
Meetings |  | 250 | 1000 | 1250 | 250 | 1000 | 1250 | 250 | 1000 | 1250 | 3750
Total |  | 150000 | 176150 | 326150 | 150000 | 154050 | 304050 | 150000 | 154050 | 304050 | 934250
Summary |  | Year 1 | Year 2 | Year 3 | Total
Grant funding |  | 150000 | 150000 | 150000 | 450000
In-kind match funding |  | 176150 | 154050 | 154050 | 484250
Total |  | 326150 | 304050 | 304050 | 934250
http://www.tellusventure.com/community/california/